## PMR
DAPITAN CITY SCHOOLS DIVISION | [9 empty] | PROCUREMENT MONITORING REPORT 2026-1ST SEMESTER (JANUARY TO JUNE 2026)
[5 empty] | Actual Procurement Activities | [13 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
| FOR SDO SECURITY SERVICES | GEORDITO OLARIO | No | SVP | N/A | 2025-11-20 | N/A | N/A | 2026-12-02 | 2026-12-02 | N/A | 2025-12-02 | 2025-12-02 | 2026-01-01 | N/A | 2025-12-15 | 2025-12-15 | MOOE | 480000 | 480000 | 0 | 477600 | 477600 | 0 | N/A | N/A | N/A | 2026-12-02 | 2026-12-02 | 2026-12-02 | 2025-12-15 | Awarded with issued Notice of Award
| Division Executive Meeting (DEXECOM) | ANALISA BAGARINAO | No | SVP | N/A | 2025-12-11 | N/A | N/A | 2025-12-15 | 2025-12-15 | N/A | 2025-12-15 | 2025-12-15 | 2026-01-01 | N/A | 2026-01-05 | 2026-01-05 | MOOE | 7000 | 7000 | 0 | 6950 | 6950 | 0 | N/A | N/A | N/A | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2026-01-05 | Completed
| DIVISION EXECUTIVE MEETING (DIVMANCOM) | NOEL P. MANGUBAT | No | SVP | N/A | 2026-01-05 | N/A | N/A | 2026-01-06 | 2026-01-06 | N/A | 2026-01-06 | 2026-01-06 | 2026-01-12 | N/A | 2026-01-22 | 2026-01-22 | MOOE | 48000 | 48000 | 0 | 48000 | 48000 | 0 | N/A | N/A | N/A | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-22 | Completed
| For the Hauling and Delivery Services of the RO-Procured FY 2025 Self-Learning Modules (SLMs) | MA. PERGA CADIENTE | No | SVP | N/A | 2026-01-13 | N/A | N/A | 2026-01-15 | 2026-01-15 | N/A | 2026-01-15 | 2026-01-15 | 2026-01-21 | N/A | 2026-04-15 | 2026-04-15 | R09-DAP-25-11-01290 | 7540 | 7540 | 0 | 6380 | 6380 | 0 | N/A | N/A | N/A | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-04-15 | Completed
| For the Implementation of Alternative Delivery Mode (ADM) | MA. PERGA CADIENTE | No | SVP | N/A | 2026-01-13 | N/A | N/A | 2026-01-15 | 2026-01-15 | N/A | 2026-01-15 | 2026-01-15 | 2026-01-21 | N/A | 2026-01-28 | 2026-01-28 | R09-DAP-25-09-01161 | 884.5 | 884.5 | 0 | 800 | 800 | 0 | N/A | N/A | N/A | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-28 | Completed
| Smoke Test for DepEd Vehicle for renewal of LTO License | BLESSYL CUENTO | No | SVP | N/A | 2026-01-13 | N/A | N/A | 2026-01-15 | 2026-01-15 | N/A | 2026-01-15 | 2026-01-15 | 2026-01-21 | N/A | 2026-02-06 | 2026-02-06 | MOOE | 900 | 900 | 0 | 450 | 450 | 0 | N/A | N/A | N/A | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-02-06 | Completed
| FOR THE USE IN PRINTING OF PAYROLLS FOR REGULAR SALARY | ARNI JAUCULAN | No | SVP | N/A | 2026-01-13 | N/A | N/A | 2026-01-15 | 2026-01-15 | N/A | 2026-01-15 | 2026-01-15 | 2026-01-21 | N/A | 2026-01-26 | 2026-01-26 | MOOE | 9100 | 9100 | 0 | 7800 | 7800 | 0 | N/A | N/A | N/A | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-26 | Completed
| Accomodation of DepEd Personnel on the Conduct of Focus Group Discussion, Orientation and Provision of Technical Assistance on the Conduct of the Computer-Based National Assessment Examination and the Conversion of SelectSchools into Implementing Units | NUEVA ANDAG | No | SVP | N/A | 2026-01-14 | N/A | N/A | 2026-01-15 | 2026-01-15 | N/A | 2026-01-15 | 2026-01-15 | 2026-01-30 | N/A | 2026-01-20 | 2026-01-20 | MOOE | 8400 | 8400 | 0 | 8400 | 8400 | 0 | N/A | N/A | N/A | 2026-01-15 | 2026-01-15 | 2026-01-15 | 2026-01-20 | Completed
| Chest Freezer units for the Supply and delivery of pasteurized milk under the SBFP- Milk Component | GWILYM ELUMBA | No | SVP | N/A | 2026-01-26 | N/A | N/A | 2026-01-28 | 2026-01-28 | N/A | 2026-01-28 | 2026-01-28 | 2026-01-30 | N/A | 2026-02-11 | 2026-02-11 | R09-DAP-25-02-0069 | 148500 | 148500 | 0 | 144900 | 144900 | 0 | N/A | N/A | N/A | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-02-11 | Completed
| SUPPLIES IN THE DEVELOPMENT IOF ECD ASSESSMENT PACKAGE | LUNA LUZ RATCHO | No | SVP | N/A | 2026-01-26 | N/A | N/A | 2026-01-28 | 2026-01-28 | N/A | 2026-01-28 | 2026-01-28 | 2026-02-27 | N/A | 2026-02-09 | 2026-02-09 | RO9-DAP-25-11-01439 | 17194 | 17194 | 0 | 17094 | 17094 | 0 | N/A | N/A | N/A | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-02-09 | Completed
| Materials for Repair of Ceiling with Water Seepage at the Office of the Division Administrative Officer,Personnel Office, Dental Office, and Men's Comfort Room | GEORDITO OLARIO | No | SVP | N/A | 2026-02-08 | N/A | N/A | 2026-02-09 | 2026-02-09 | N/A | 2026-02-09 | 2026-02-09 | 2026-02-11 | N/A | 2026-03-26 | 2026-03-26 | MOOE | 19315 | 19315 | 0 | 19100 | 19100 | 0 | N/A | N/A | N/A | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-03-26 | Completed
| For the Supply and Delivery of Aircon 2HP, Inverter, Window Type for CID Chief to reduce indoor temperature and to keep them and to maintain a comfortable working environment. | VICENTE JOSE SUAREZ II | No | SVP | N/A | 2026-02-02 | N/A | N/A | 2026-02-09 | 2026-02-09 | N/A | 2026-02-09 | 2026-02-09 | 2026-02-11 | N/A | 2026-02-11 | 2026-02-11 | MOOE | 62325 | 62325 | 0 | 62235 | 62235 | 0 | N/A | N/A | N/A | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-11 | Completed
| PRINTING OF REGULAR PAYROLL, PAYSLIP AND FORM 7 | ARNI JAUCULAN | No | SVP | N/A | 2026-02-07 | N/A | N/A | 2026-03-03 | 2026-03-03 | N/A | 2026-03-03 | 2026-03-03 | 2026-02-18 | N/A | 2026-02-27 | 2026-02-27 | MOOE | 22900 | 22900 | 0 | 22900 | 22900 | 0 | N/A | N/A | N/A | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-02-27 | Completed
| for the Division Executive Committee Meeting cum Training-Workshop on the Use of Electronic Systems: SOS, DepEd | ANALISA BAGARINAO | No | SVP | N/A | 2026-02-19 | N/A | N/A | 2026-02-24 | 2026-02-24 | N/A | 2026-02-24 | 2026-02-24 | 2026-02-27 | N/A | 2026-03-03 | 2026-03-03 | MOOE | 7000 | 7000 | 0 | 7000 | 7000 | 0 | N/A | N/A | N/A | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-03-03 | Completed
| Program Implementation Review on ARAL -Reading Program | ANALISA BAGARINAO | No | SVP | N/A | 2026-02-26 | N/A | N/A | 2026-03-04 | 2026-03-04 | N/A | 2026-03-04 | 2026-03-04 | 3/10/2026 | N/A | 2026-05-04 | 2026-05-04 | R09-DAP-25-08-01112 | 186000 | 186000 | 0 | 178250 | 178250 | 0 | N/A | N/A | N/A | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-05-04 | Completed
| SEND PROGRAM IMPLEMENTATION | ELSA ARANAS | No | SVP | N/A | 2026-03-04 | N/A | N/A | 2026-03-10 | 2026-03-10 | N/A | 2026-03-10 | 2026-03-10 | 2026-03-19 | N/A | 2026-03-31 | 2026-03-31 | R09-DAP-25-03-0183 | 6480 | 6480 | 0 | 5900 | 5900 | 0 | N/A | N/A | N/A | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-31 | Completed
| COA EXIT CONFERENCE | GEORDITO OLARIO | No | SVP | N/A | 2026-03-02 | N/A | N/A | 2026-03-03 | 2026-03-03 | N/A | 2026-03-03 | 2026-03-03 | 2026-03-10 | N/A | 2026-03-10 | 2026-03-10 | MOOE | 14000 | 14000 | 0 | 14000 | 14000 | 0 | N/A | N/A | N/A | 2026-03-03 | 2026-03-03 | 2026-03-03 | 2026-03-10 | Completed
| Cleaning of Airconditioned Units (regular maintenance) | BLESSYL CUENTO | No | SVP | N/A | 2026-03-04 | N/A | N/A | 2026-03-10 | 2026-03-10 | N/A | 2026-03-10 | 2026-03-10 | 2026-03-10 | N/A | 2026-03-23 | 2026-03-23 | MOOE | 21300 | 21300 | 0 | 21300 | 21300 | 0 | N/A | N/A | N/A | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-23 | Completed
| Program Implementation Review on ARAL-Reading Phase II | ANALISA BAGARINAO | No | SVP | N/A | 2026-03-10 | N/A | N/A | 2026-03-13 | 2026-03-13 | N/A | 2026-03-13 | 2026-03-13 | 2026-03-19 | N/A | 2026-05-25 | 2026-05-25 | R09-DAP-25-08-01112 | 67200 | 67200 | 0 | 67000 | 67000 | 0 | N/A | N/A | N/A | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-05-25 | Completed
| For Printing of Form 7, Payslips and Remittances | ARNI JAUCULAN | No | SVP | N/A | 2026-03-04 | N/A | N/A | 2026-03-13 | 2026-03-13 | N/A | 2026-03-13 | 2026-03-13 | 2026-03-19 | N/A | 2026-03-25 | 2026-03-25 | MOOE | 23450 | 23450 | 0 | 23450 | 23450 | 0 | N/A | N/A | N/A | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-25 | Completed
| For Document Scanning in Records Office | CYNTHIA DALMAN | No | SVP | N/A | 2026-03-24 | N/A | N/A | 2026-04-06 | 2026-04-06 | N/A | 2026-04-06 | 2026-04-06 | 2026-04-13 | N/A | 2026-04-20 | 2026-04-20 | MOOE | 35000 | 35000 | 0 | 34990 | 34990 | 0 | N/A | N/A | N/A | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-20 | Completed
| Coffee Brewer machine for ASDS Office | AURELIO SANTISAS | No | SVP | N/A | 2026-03-12 | N/A | N/A | 2026-04-06 | 2026-04-06 | N/A | 2026-04-06 | 2026-04-06 | 2026-04-13 | N/A | 2026-04-21 | 2026-04-21 | MOOE | 2500 | 2500 | 0 | 2500 | 2500 | 0 | N/A | N/A | N/A | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-21 | Completed
| REPAIR/INSTALLATION OF CIRCUIT BREAKER | BLESSYL CUENTO | No | SVP | N/A | 2026-03-12 | N/A | N/A | 2026-03-13 | 2026-03-13 | N/A | 2026-03-13 | 2026-03-13 | 2026-04-13 | N/A | 2026-03-26 | 2026-03-26 | MOOE | 1000 | 1000 | 0 | 1000 | 1000 | 0 | N/A | N/A | N/A | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-26 | Completed
| Room Rental for ASDS Room Accommodation | AURELIO SANTISAS | No | SVP | N/A | 2026-03-12 | N/A | N/A | 2026-03-13 | 2026-03-13 | N/A | 2026-03-13 | 2026-03-13 | 2026-03-19 | N/A | 2026-03-24 | 2026-03-24 | MOOE | 120000 | 120000 | 0 | 120000 | 120000 | 0 | N/A | N/A | N/A | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-24 | Completed
| DRINKING WATER FOR SDO OFFICES | BLESSYL CUENTO | No | SVP | N/A | 2026-03-12 | N/A | N/A | 2026-04-06 | 2026-04-06 | N/A | 2026-04-06 | 2026-04-06 | 2026-04-13 | N/A | 2026-04-20 | 2026-04-20 | MOOE | 6000 | 6000 | 0 | 6000 | 6000 | 0 | N/A | N/A | N/A | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-20 | Completed
| FOR REPAINTING AND SURFACE REFURBISHMENT OF THE SCHOOLS DIVISION OFFICE MAIN LOBBY | BLESSYL CUENTO | No | SVP | N/A | 2026-03-18 | N/A | N/A | 2026-04-06 | 2026-04-06 | N/A | 2026-04-06 | 2026-04-06 | 2026-04-13 | N/A | 2026-05-07 | 2026-05-07 | MOOE | 13710 | 13710 | 0 | 13196 | 13196 | 0 | N/A | N/A | N/A | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-05-07 | Completed
| For the Hauling and Delivery Services of the RO - Procured FY 2025 Self Learning Modules | MA. PERGA CADIENTE | No | SVP | N/A | 2026-03-18 | N/A | N/A | 2026-05-05 | 2026-05-05 | N/A | 2026-05-05 | 2026-05-05 | 2026-04-13 | N/A | 2026-06-25 | 2026-06-25 | R09-DAP-25-11-01290 | 1165.45 | 1165.45 | 0 | 1157 | 1157 | 0 | N/A | N/A | N/A | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-06-25 | Completed
| For the Implementation of Alternative Delivery Mode (ADM) | MA. PERGA CADIENTE | No | SVP | N/A | 2026-03-18 | N/A | N/A | 2026-04-06 | 2026-04-06 | N/A | 2026-04-06 | 2026-04-06 | 2026-04-13 | N/A | 2026-04-21 | 2026-04-21 | R09-DAP-25-09-01161 | 84.99 | 84.99 | 0 | 84.99 | 84.99 | 0 | N/A | N/A | N/A | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-21 | Completed
| For DepEd Vehicle VAN Maintenance | BLESSYL CUENTO | No | SVP | N/A | 2026-03-18 | N/A | N/A | 2026-04-06 | 2026-04-06 | N/A | 2026-04-06 | 2026-04-06 | 2026-04-13 | N/A | 2026-05-07 | 2026-05-07 | MOOE | 30880 | 30880 | 0 | 30795 | 30795 | 0 | N/A | N/A | N/A | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-05-07 | Completed
| For the use in the General Services Unit | BLESSYL CUENTO | No | SVP | N/A | 2026-03-24 | N/A | N/A | 2026-04-06 | 2026-04-06 | N/A | 2026-04-06 | 2026-04-06 | 2026-04-13 | N/A | 2026-04-21 | 2026-04-21 | MOOE | 36525 | 36525 | 0 | 36400 | 36400 | 0 | N/A | N/A | N/A | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-21 | Completed
| Division Executive Meeting cum Capability-Building Session on the Personnel Information Empowerment | ANALISA BAGARINAO | No | SVP | N/A | 2026-03-24 | N/A | N/A | 2026-04-06 | 2026-04-06 | N/A | 2026-04-06 | 2026-04-06 | 2026-04-13 | N/A | 2026-04-15 | 2026-04-15 | MOOE | 7000 | 7000 | 0 | 7000 | 7000 | 0 | N/A | N/A | N/A | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-15 | Completed
| Procurement of Laptop for the use of SBFP COS | GWILYM ELUMBA | No | SVP | N/A | 2026-04-21 | N/A | N/A | 2026-04-22 | 2026-04-22 | N/A | 2026-04-22 | 2026-04-22 | 2026-04-27 | N/A | 2026-05-13 | 2026-05-13 | R09-DAP-25-02-0069 | 45500 | 45500 | 0 | 43000 | 43000 | 0 | N/A | N/A | N/A | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-05-13 | Completed
| FOR CHANGE OIL OF MITSUBISHI PICK-UP | BLESSYL C. CUENTO | No | SVP | N/A | 2026-04-16 | N/A | N/A | 2026-04-21 | 2026-04-21 | N/A | 2026-04-21 | 2026-04-21 | 2026-04-27 | N/A | 2026-04-30 | 2026-04-30 | MOOE | 35336 | 35336 | 0 | 35336 | 35336 | 0 | N/A | N/A | N/A | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-04-30 | Completed
| To be used for DepEd Dapitan City service vehicles. | BLESSYL C. CUENTO | No | SVP | N/A | 2026-04-16 | N/A | N/A | 2026-04-21 | 2026-04-21 | N/A | 2026-04-21 | 2026-04-21 | 2026-04-27 | N/A | 2026-06-25 | 2026-06-25 | MOOE | 75000 | 75000 | 0 | 50000 | 50000 | 0 | N/A | N/A | N/A | 2026-04-21 | 2026-04-21 | 2026-04-21 | 2026-06-25 | Completed
| Supply and delivery of meals and snacks good for 2 days for the participants of Division Orientation on SBFP Implementation SY 2026-2027 | GWILYM C. ELUMBA | No | SVP | N/A | 2026-04-27 | N/A | N/A | 2026-05-04 | 2026-05-04 | N/A | 2026-05-04 | 2026-05-04 | 2026-05-06 | N/A | 2026-05-18 | 2026-05-18 | R09-DAP-26-04-0272 | 70500 | 70500 | 0 | 66840 | 66840 | 0 | N/A | N/A | N/A | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-18 | Completed
| Supply and delivery TARPAULIN for the participants of Division Orientation on SBFP Implementation SY 2026-2027 | GWILYM C. ELUMBA | No | SVP | N/A | 2026-05-04 | N/A | N/A | 2026-05-06 | 2026-05-06 | N/A | 2026-05-06 | 2026-05-06 | 2026-05-07 | N/A | 2026-05-19 | 2026-05-19 | R09-DAP-26-04-0272 | 900 | 900 | 0 | 740 | 740 | 0 | N/A | N/A | N/A | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-19 | Completed
| For procurement office use | MICHAEL E. TAN | No | SVP | N/A | 2026-05-04 | N/A | N/A | 2026-05-06 | 2026-05-06 | N/A | 2026-05-06 | 2026-05-06 | 2026-05-06 | N/A | 2026-05-18 | 2026-05-18 | MOOE | 49500 | 49500 | 0 | 49500 | 49500 | 0 | N/A | N/A | N/A | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-18 | Completed
| FOR THE USE OF CID OFFICE | VICENTE JOSE SUAREZ II | No | SVP | N/A | 2026-05-04 | N/A | N/A | 2026-05-06 | 2026-05-06 | N/A | 2026-05-06 | 2026-05-06 | 2026-05-04 | N/A | 2026-05-19 | 2026-05-19 | MOOE | 195980 | 195980 | 0 | 195980 | 195980 | 0 | N/A | N/A | N/A | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-19 | Completed
| FOR ADMINISTRATIVE SERVICE UNIT USE | GEORDITO T. OLARIO | No | SVP | N/A | 2026-05-04 | N/A | N/A | 2026-05-06 | 2026-05-06 | N/A | 2026-05-06 | 2026-05-06 | 2026-05-07 | N/A | 2026-06-01 | 2026-06-01 | OPDNTP | 696.25 | 696.25 | 0 | 630 | 630 | 0 | N/A | N/A | N/A | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-06-01 | Completed
| DIVMANCOM | NOEL P. MANGUBAT | No | SVP | N/A | 2026-05-03 | N/A | N/A | 2026-05-05 | 2026-05-05 | N/A | 2026-05-05 | 2026-05-05 | 2026-05-06 | N/A | 2026-06-15 | 2026-06-15 | MOOE | 54000 | 54000 | 0 | 49950 | 49950 | 0 | N/A | N/A | N/A | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-06-15 | Completed
| ARAL SUMMER PROGRAM | ANALISA A. BAGARINAO | No | SVP | N/A | 2026-05-11 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-06-18 | 2026-06-18 | RO-9-DAP-26-04-0377 | 80000 | 80000 | 0 | 77375 | 77375 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-06-18 | Completed
| Capacity Building on Basic Life Support and First Aid for Healthy Learning Institutions (HLIs) of the Schools division of Dapitan City. | JONATHAN RELUYA | No | SVP | N/A | 2026-05-04 | N/A | N/A | 2026-05-06 | 2026-05-06 | N/A | 2026-05-06 | 2026-05-06 | 2026-05-07 | N/A | 2026-05-25 | 2026-05-25 | DRRM-DPRP | 19725 | 19725 | 0 | 19545 | 19545 | 0 | N/A | N/A | N/A | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-25 | Completed
| Capacity Building on Basic Life Support and First Aid for Healthy Learning Institutions (HLIs) of the Schools division of Dapitan City. | JONATHAN RELUYA | No | SVP | N/A | 2026-05-04 | N/A | N/A | 2026-05-06 | 2026-05-06 | N/A | 2026-05-06 | 2026-05-06 | 2026-05-07 | N/A | 2026-05-25 | 2026-05-25 | DRRM-DPRP | 195980 | 195980 | 0 | 152745 | 152745 | 0 | N/A | N/A | N/A | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-25 | Completed
| SUPPORT TO SNED PROGRAM IMPLEMENTATION | ELSA ARANAS | No | SVP | N/A | 2026-05-11 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-06-08 | 2026-06-08 | RO-9-DAP-26-07-0966 | 3720 | 3720 | 0 | 3720 | 3720 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-06-08 | Completed
| Office Supply for Re-Echo on Universal Prevention Curriculum for Substance | SILVAN ELMER S. GEMPEROSO | No | SVP | N/A | 2026-05-11 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-06-11 | 2026-06-11 | DAP-25-08-01032 | 1100 | 1100 | 0 | 1080 | 1080 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-06-11 | Completed
| Procurement of Office Supplies and Equipment for SDS office. | BLESSYL CUENTO | No | SVP | N/A | 2026-05-11 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-06-11 | 2026-06-11 | MOOE | 20615 | 20615 | 0 | 20615 | 20615 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-06-11 | Completed
| Procurement of Bath Soap for SBFP feeding benefeciaries, SBFP implementation SY 2026-2027 | GWILYM C. ELUMBA | No | SVP | N/A | 2026-05-12 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-06-11 | 2026-06-11 | RO-9-DAP-26-04-0272 | 101040 | 101040 | 0 | 101040 | 101040 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-06-11 | Completed
| Supply and Delivery of Load Card | GWILYM C. ELUMBA | No | SVP | N/A | 2026-05-12 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-05-25 | 2026-05-25 | RO-9-DAP-26-04-0272 | 12000 | 12000 | 0 | 12000 | 12000 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-25 | Completed
| For ARAL-Reading (summer remediation program) monitoring | ANALISA A. BAGARINAO | No | SVP | N/A | 2026-05-12 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 5/225/2026 | 5/225/2026 | R09-Dap-25-08-01112 | 19725 | 19725 | 0 | 3600 | 3600 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 5/225/2026 | Completed
| Athelete's Training and Preparation in the 2026 Palarong Pambansa | NOEL P. MANGUBAT | No | SVP | N/A | 2026-05-12 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-06-09 | 2026-06-09 | SUB-Aro NO. OSEC-9-25-04476 | 36940 | 36940 | 0 | 30380 | 30380 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-06-09 | Completed
| Athelete's Training and Preparation in the 2026 Palarong Pambansa | NOEL P. MANGUBAT | No | SVP | N/A | 2026-05-12 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-05-18 | 2026-05-18 | SUB-Aro NO. OSEC-9-25-04476 | 153000 | 153000 | 0 | 30380 | 30380 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | Completed
| The Philippines, situated along the Pacific Ring of Fire and the Typhoon Belt, is prone to natural hazards such as typhoons, earthquakes, volcanic eruptions and tsunamis. Furthermore, human-induced hazards such as crimes, | NOEL P. MANGUBAT | No | SVP | N/A | 2026-05-18 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-05-25 | 2026-05-25 | SUB-Aro RO.-9-DAP-26-04-0264 and HRD INSET GAA Funds | 59562.5 | 59562.5 | 0 | 59562.5 | 59562.5 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-25 | Completed
| Division-Led Training on the Revised Grades 6 & TLE Grade 9 & 10 Curriculum | NOEL P. MANGUBAT | No | SVP | N/A | 2026-05-11 | N/A | N/A | 2026-05-15 | 2026-05-15 | N/A | 2026-05-15 | 2026-05-15 | 2026-05-20 | N/A | 2026-05-26 | 2026-05-26 | SUB-Aro RO.-9-DAP-26-04-0264 and HRD INSET GAA Funds | 1701000 | 1701000 | 0 | 1485540 | 1485540 | 0 | N/A | N/A | N/A | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-26 | Completed
| BRIGADA ESKWELA | RENE ACABAL | No | SVP | N/A | 2026-05-20 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-02 | N/A | 2026-05-29 | 2026-05-29 | MOOE 5021 408 000 - OSEC-9-26-01760 | 50000 | 50000 | 0 | 50000 | 50000 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-29 | Completed
| BRIGADA ESKWELA | RENE ACABAL | No | SVP | N/A | 2026-05-20 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-02 | N/A | 2026-05-29 | 2026-05-29 | MOOE 5021 408 000 - OSEC-9-26-01760 | 5060 | 5060 | 0 | 5060 | 5060 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-29 | Completed
| ORIENTATION ON PLANSMART FOR SAFE SCHOOLS PROJECT (PSSS) CUM M7X READY | JONATHAN RELUYA | No | SVP | N/A | 2026-05-20 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-02 | N/A | 2026-06-22 | 2026-06-22 | DRRM-DPRP | 18593.75 | 18593.75 | 0 | 18493.75 | 18493.75 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-22 | Completed
| ORIENTATION ON PILLAR I GUIDEBOOK OF THE COMPREHENSIVE SCHOOL SAFETY FRAMEWORK (CSSF) | JONATHAN RELUYA | No | SVP | N/A | 2026-05-20 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-02 | N/A | 2026-06-22 | 2026-06-22 | DRRM-DPRP | 126000 | 126000 | 0 | 126000 | 126000 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-22 | Completed
| Using it for official ceremonies and for use in the division office. | BLESSYL C. CUENTO | No | SVP | N/A | 2026-05-21 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-02 | N/A | 2026-06-04 | 2026-06-04 | MOOE | 6600 | 6600 | 0 | 6600 | 6600 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-04 | Completed
| MAINTENANCE AND TECHNICAL SUPPORT SERVICES | LOURENCE N. REYES | No | SVP | N/A | 2026-05-21 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-02 | N/A | 2026-06-10 | 2026-06-10 | MOOE | 48695 | 48695 | 0 | 48687 | 48687 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-10 | Completed
| Division Executive Committee Meeting Cum Orientation on the ICT Equipment Information System and Utilization of the SEF | ANALISA A. BAGARINAO | No | SVP | N/A | 2026-05-21 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-02 | N/A | 2026-06-02 | 2026-06-02 | MOOE | 7000 | 7000 | 0 | 7000 | 7000 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-02 | Completed
| Provision of supplies and materials for Alternative Learning System (ALS) learners for school-Year 2026-2027 | MA. PERGA CADIENTE | No | SVP | N/A | 2026-05-25 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-02 | N/A | 2026-06-24 | 2026-06-24 | RO-9-DAP-26-05-0487 | 100000 | 100000 | 0 | 99949 | 99949 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-24 | Completed
| For ARAL-Reading (summer remediation program) monitoring | MA. PERGA CADIENTE | No | SVP | N/A | 2026-05-20 | N/A | N/A | 2026-06-02 | 2026-06-02 | N/A | 2026-06-02 | 2026-06-02 | 2026-06-10 | N/A | 2026-06-15 | 2026-06-15 | R09-Dap-25-08-01112 | 916050 | 916050 | 0 | 3600 | 3600 | 0 | N/A | N/A | N/A | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-15 | Completed
| Re-Orientation of Grade One Teachers on the Administration of Multi-Factored Assessment Tool (MFAT) | ELSA ARANAS | No | SVP | N/A | 2026-05-21 | N/A | N/A | 2026-06-02 | 2026-06-02 | N/A | 2026-06-02 | 2026-06-02 | 2026-06-10 | N/A | 2026-06-27 | 2026-06-27 | RO-9-DAP-26-04-0391 | 40200 | 40200 | 0 | 36850 | 36850 | 0 | N/A | N/A | N/A | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-27 | Completed
| BRIGADA ESKWELA | RENE ACABAL | No | SVP | N/A | 2026-05-20 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 |  | N/A | 2026-06-08 | 2026-06-08 | MOOE 5021 408 000 - OSEC-926-01760 | 7000 | 7000 | 0 | 6830 | 6830 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-08 | Completed
| 1st Quarter - For the office use and operational supplies and items of various office and sections within the Schools Division Office of Dapitan City. | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-22 | 2026-06-22 | MOOE | 983373 | 983373 | 0 | 98185 | 98185 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-22 | Completed
| FOR EFFICIENT WORK AND COMFORT INSIDE THE OFFICE | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-23 | 2026-06-23 | MOOE | 6500 | 6500 | 0 | 6500 | 6500 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-23 | Completed
| To provide the personnel, teachers, and visiting clients of the Schools Division Office with continuous, safe, and easily accessible drinking water. | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-23 | 2026-06-23 | MOOE | 8200 | 8200 | 0 | 8100 | 8100 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-23 | Completed
| To provide the personnel, teachers, and visiting clients of the Schools Division Office with continuous, safe, and easily accessible drinking water. | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-19 | 2026-06-19 | MOOE | 8500 | 8500 | 0 | 8100 | 8100 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-19 | Completed
| Procurement of Uninterruptible Power Supply (UPS) Units for Office Desktops and Server Equipment. | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-23 | 2026-06-23 | MOOE | 4217.44 | 4217.44 | 0 | 4215 | 4215 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-23 | Completed
| Procurement of High-Definition LED Computer Monitors for the Schools Division Office. | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-23 | 2026-06-23 | MOOE | 5000 | 5000 | 0 | 5000 | 5000 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-23 | Completed
| Procurement of 2 HP Split Type Inverter Air Conditioning Units for the Schools Division Office. | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-24 | 2026-06-24 | MOOE | 50000 | 50000 | 0 | 50000 | 50000 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-24 | Completed
| Procurement of Ergonomic Executive Office Chairs | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-23 | 2026-06-23 | MOOE | 6000 | 6000 | 0 | 6000 | 6000 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-23 | Completed
| Procurement of Normal, Heavy-Duty Hot and Cold Water Dispensers for the Schools Division Office. | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-23 | 2026-06-23 | MOOE | 7000 | 7000 | 0 | 7000 | 7000 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-23 | Completed
| Procurement of Clerical Mesh Office Chairs for the Schools Division Office Staff. | JIDELLE GARCIA | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-23 | 2026-06-23 | MOOE | 14900 | 14900 | 0 | 14900 | 14900 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-23 | Completed
| For printing of pertinent documents and other personnel related functions. | AMYTHYST FAITH DIAO | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A | 2026-06-24 | 2026-06-24 | MOOE | 16995 | 16995 | 0 | 16995 | 16995 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-24 | Completed
| PURCHASE OF ELECTRICAL MATERIALS TO BE USED IN DIVISION OFFICE. | BLESSYL C. CUENTO | No | SVP | N/A | 2026-05-18 | N/A | N/A | 2026-06-17 | 2026-06-17 | N/A | 2026-06-17 | 2026-06-17 | 2026-06-23 | N/A | 2026-07-02 | 2026-07-02 | MOOE | 11720 | 11720 | 0 | 10175 | 10175 | 0 | N/A | N/A | N/A | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-07-02 | Completed
| Procurement of Banner in replacement and submission of the Division Office Banner | BLESSYL C. CUENTO | No | SVP | N/A | 2026-06-04 | N/A | N/A | 2026-06-17 | 2026-06-17 | N/A | 2026-06-17 | 2026-06-17 | 2026-06-23 | N/A | 2026-07-02 | 2026-07-02 | MOOE | 6400 | 6400 | 0 | 5600 | 5600 | 0 | N/A | N/A | N/A | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-07-02 | Completed
| FOR RECORDS AND PERSONNEL OFFICE USE | CYNTHIA DALMAN | No | SVP | N/A | 2026-06-04 | N/A | N/A | 2026-06-17 | 2026-06-17 | N/A | 2026-06-17 | 2026-06-17 | 2026-06-23 | N/A | 2026-07-01 | 2026-07-01 | MOOE | 10000 | 10000 | 0 | 9550 | 9550 | 0 | N/A | N/A | N/A | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-07-01 | Completed
| Supply and Delivery of Keyed Entry Door Knob Handle Type (Silver Stainless Steel) for ASDS Office security entry | AURELIO SANTISAS | No | SVP | N/A | 2026-06-11 | N/A | N/A | 2026-06-17 | 2026-06-17 | N/A | 2026-06-17 | 2026-06-17 | 2026-06-23 | N/A | 2026-06-29 | 2026-06-29 | MOOE | 1420 | 1420 | 0 | 1420 | 1420 | 0 | N/A | N/A | N/A | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-29 | Completed
| Provide accessible and clean drinking water for office staff and visitors, which is essential for maintaining health, productivity, and professional hospitality during meetings | JIDELLE GARCIA | No | SVP | N/A | 2026-06-11 | N/A | N/A | 2026-06-17 | 2026-06-17 | N/A | 2026-06-17 | 2026-06-17 | 2026-06-23 | N/A | 2026-06-30 | 2026-06-30 | MOOE | 6500 | 6500 | 0 | 6500 | 6500 | 0 | N/A | N/A | N/A | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-30 | Completed
| To secure backup and management of essential digital files, reports, and administrative data | JIDELLE GARCIA | No | SVP | N/A | 2026-06-11 | N/A | N/A | 2026-06-17 | 2026-06-17 | N/A | 2026-06-17 | 2026-06-17 | 2026-06-23 | N/A | 2026-07-02 | 2026-07-02 | MOOE | 9600 | 9600 | 0 | 9600 | 9600 | 0 | N/A | N/A | N/A | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-07-02 | Completed
| Provide necessary cabling and connectivity hardware for the installation, repair, and expansion of the office network, ensuring secure and consistent internet access for all workstations and administrative systems. | JIDELLE GARCIA | No | SVP | N/A | 2026-06-11 | N/A | N/A | 2026-06-17 | 2026-06-17 | N/A | 2026-06-17 | 2026-06-17 | 2026-06-23 | N/A | 2026-06-29 | 2026-06-29 | MOOE | 24790 | 24790 | 0 | 24790 | 24790 | 0 | N/A | N/A | N/A | 2026-06-17 | 2026-06-17 | 2026-06-17 | 2026-06-29 | Completed
N/A
[18 empty] | Total Allotted Budget of Procurement Activities | 6849487.88 | 6849487.88 | 0
[18 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 4583890.24 | 4583890.24 | 0
[18 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 2265597.64
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
ONGOING PROCUREMENT ACTIVITIES
| ORIENTATION ON PLANSMART FOR SAFE SCHOOLS PROJECT (PSSS) CUM M7X READY | JONATHAN RELUYA | No | SVP | N/A | 2026-05-20 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-01 | N/A |  |  | DRRM-DPRP | 152400 | 152400 | 0 | 152400 | 152400 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25
| ORIENTATION ON PILLAR I GUIDEBOOK OF THE COMPREHENSIVE SCHOOL SAFETY FRAMEWORK | JONATHAN RELUYA | No | SVP | N/A | 2026-05-20 | N/A | N/A | 2026-05-25 | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-01 | N/A |  |  | DRRM-DPRP | 17562.5 | 17562.5 | 0 | 17462.5 | 17462.5 | 0 | N/A | N/A | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25
| Seminar-Workshop on Strengthening Teacher Instruction in Kindergarten and Across Learning Areas | VICENTE RAMON SUAREZ II | No | SVP | N/A | 2026-05-25 | N/A | N/A | 2026-06-02 | 2026-06-02 | N/A | 2026-06-02 | 2026-06-02 | 2026-06-10 | N/A |  |  | GAA HRD | 400800 | 400800 | 0 | 347360 | 347360 | 0 | N/A | N/A | N/A | 2026-06-02 | 2026-06-02 | 2026-06-02
| Training of Teachers on Digital Generative AI Literacy | VICENTE RAMON SUAREZ II | No | SVP | N/A | 2026-05-25 | N/A | N/A | 2026-06-02 | 2026-06-02 | N/A | 2026-06-02 | 2026-06-02 | 2026-06-10 | N/A |  |  | GAA HRD | 66000 | 66000 | 0 | 60500 | 60500 | 0 | N/A | N/A | N/A | 2026-06-02 | 2026-06-02 | 2026-06-02 |  | Awarded with issued Notice of Award
| 2026 INTENSIVE SEMINAR-WORKSHOP ON RESEARCH INNOVATIONS AND EXHIBITS | VICENTE RAMON SUAREZ II | No | SVP | N/A | 2026-06-01 | N/A | N/A | 2026-06-08 | 2026-06-08 | N/A | 2026-06-08 | 2026-06-08 | 2026-06-11 | N/A |  |  | GAA HRD | 60000 | 60000 | 0 | 55000 | 55000 | 0 | N/A | N/A | N/A | 2026-06-08 | 2026-06-08 | 2026-06-08 |  | Awarded with issued Notice of Award
| Accommodation must be located within 1 km radius from Bulwagan ng Katarungan, venue of hearing. (State Solicitor of the OSG representing DepEd in Civil Case No 7801) | TRIZIA GLAE CHAN | No | SVP | N/A | 2026-01-22 | N/A | N/A | 2026-01-28 | 2026-01-28 | N/A | 2026-01-28 | 2026-01-28 | 2026-01-30 | N/A |  |  | MOOE | 13200 | 13200 | 0 | 13200 | 13200 | 0 | N/A | N/A | N/A | 2026-01-28 | 2026-01-28 | 2026-01-28 |  | Awarded with issued Notice of Award
| Plaque of Appreciation for Retirees | BLESSYL CUENTO | No | SVP | N/A | 2026-02-24 | N/A | N/A | 2026-02-25 | 2026-02-25 | N/A | 2026-02-25 | 2026-02-25 | 2026-02-27 | N/A |  |  | MOOE | 15000 | 15000 | 0 | 14700 | 14700 | 0 | N/A | N/A | N/A | 2026-02-25 | 2026-02-25 | 2026-02-25 |  | Awarded with issued Notice of Award
| For the Conduct of Division IPEd Summit 2026 | JEPHONE P. YORONG | No | SVP | N/A | 2026-04-16 | N/A | N/A | 2026-04-21 | 2026-04-21 | N/A | 2026-04-21 | 2026-04-21 | 2026-04-27 | N/A |  |  | R09-DAP-25-04-0513 | 90000 | 90000 | 0 | 90000 | 90000 | 0 | N/A | N/A | N/A | 2026-04-21 | 2026-04-21 | 2026-04-21 |  | Awarded with issued Notice of Award
| FOR THE CONDUCT OF DIVISION FESTIVAL OF TALENTS (DFOT) | JEPHONE YORONG | No | SVP | N/A | 4/22/22026 | N/A | N/A | 2026-05-04 | 2026-05-04 | N/A | 2026-05-04 | 2026-05-04 | 5/6/2026 | N/A |  |  | R09-DAP-26-03-0216 | 49800 | 49800 | 0 | 44820 | 44820 | 0 | N/A | N/A | N/A | 2026-05-04 | 2026-05-04 | 2026-05-04 |  | Awarded with issued Notice of Award
[18 empty] | Total Allotted Budget of On-going Procurement Activities | 864762.5 | 864762.5 | 0 | 795442.5 | 795442.5 | 0
|  | Prepared by: | [7 empty] | Recommended for Approval by: | [11 empty] | APPROVED:
|  | MICHAEL E. TAN, MPA | [7 empty] | AURELIO A. SANTISAS, CESO VI | [11 empty] | JAY S. MONTEALTO, CESO V
|  | Administrative Officer IV | [7 empty] | Assistant Schools Division Superintendent | [11 empty] | Schools Division Superintendent
|  | Head, BAC Secretariat | [7 empty] | BAC Chairperson | [11 empty] | Head of Procuring Entity

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds | Mode of Procurement
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget) | Competitive Bidding
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget) | Limited Source Bidding
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget) | Direct Contracting
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution | Repeat Order
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution | Shopping 52.1(a) - Unforeseen Contingency
Failed under Section 35.1 (b) |  | BAC Resolution |  | Shopping 52.1(b) - Regular Office Supplies and Equipment not available in PS
Failed under Section 35.1 (c) |  | Award |  | Negotiated Procurement - Two Failed Biddings
Failed under Section 41 (b) |  | Cancelled |  | Negotiated Procurement - Emergency Cases
Failed under Section 41 (c) |  |  |  | Negotiated Procurement - Take-Over of Contracts
Contract was extended |  |  |  | Negotiated Procurement - Adjacent or Contiguous
Contract was renewed |  |  |  | Negotiated Procurement - Agency-to-Agency
Cancelled |  |  |  | Negotiated Procurement - Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
Others, please encode directly on the cell |  |  |  | Negotiated Procurement - Highly Technical Consultants
Negotiated Procurement - Defense Cooperation Agreement
Negotiated Procurement - Small Value Procurement
Negotiated Procurement - Lease of Real Property and Venue
Negotiated Procurement - NGO Participation
Negotiated Procurement - Community Participation
Negotiated Procurement - UN Agencies, Int'l Organizations or International Financing Institutions
Negotiated Procurement - Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant Products, Electronic Charging Devices, and Online Subscriptions
Foreign Guidelines - Competitive Bidding
Foreign Guidelines - Alternative Method
Competitive Dialogue
Unsolicited Offer with Bid Matching
Direct Acquisition
Direct Sales
Direct Procurement for Science, Technology, and Innovation
Others, specify in the remarks: Mode of Procurement use <Mode>